## Monthly report
PROJECT NAME : BRAVE WOMEN
ORGANIZATION : Maison de l’Entreprise du Burkina Faso (MEBF)
11 BP 379 OUAGADOUGOU 11 TEL 00226 25 39 80 60 /61
REPORTING PERIOD : 01/JANUARY 2021 to 31/DECEMBER 2022
USD/CFA (as of 21 June 2022)
630 | [5 empty] | STATEMENT OF FINANCIAL POSITION
CODE | BUDGET COMPONENTS/TOTAL | CFA | USD (A) | Inception To DECEMBER (B) 2022 | Expenditure 2021 | Expenditure 2022 (USD) | [11 empty] | CUMMUL TO 31/12/2022 (USD) | VARIANCE (USD) (C=A-B) | RATE D=B/A
[6 empty] | January | Febrary | mars | April | mai | June | July | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBRE
|  | 1100457449.1194 | 1746757.8557 | 489730.3812 | 67.8735 | 0 | 9.5983 | 29895.8991 | 39556.1966 | 38665.359 | 64992.6291 | 36119.788 | 22663.2752 | 46192.3197 | 56498.3282 | 32470.1026 | 122599.012 | 489662.5077 | 1257095.3481 | 0.28033
Component 1: Business Resilience Capacity Building
11001 | Capacity building workshops (27) | 110795040 | 175865.1429 | 136038.2735 |  | Expenditure 2022 (USD) OCTOBER: 29371.0085; Expenditure 2022 (USD) NOVEMBER: 9035.7265; Expenditure 2022 (USD) DECEMBRE: 97631.5385 | 136038.2735 | 39826.8694 | 77.35%
11002 | workshop / recruitment of consultants (1) | 2060000 | 3269.8413 | 3257.7778 |  | Expenditure 2022 (USD) SEPTEMBER: 605.812; Expenditure 2022 (USD) OCTOBER: 605.812; Expenditure 2022 (USD) DECEMBRE: 2046.1538 | 3257.7778 | 12.0635 | 99.63%
11003 | workshop / Upgrading consultants (1) for training | 712760 | 1131.3651 | 0 | [13 empty] | 0 | 1131.3651 | 0%
11004 | launch workshop (1) | 2832500 | 4496.0317 | 4541.8803 |  | Expenditure 2022 (USD) June: 1100; Expenditure 2022 (USD) July: 2064.9573; Expenditure 2022 (USD) SEPTEMBER: 987.735; Expenditure 2022 (USD) OCTOBER: 377.2222; Expenditure 2022 (USD) NOVEMBER: 11.9658 | 4541.8803 | -45.8486 | 101%
11005 | Central region workshop (1) | 618000 | 980.9524 | 512.8205 |  | Expenditure 2022 (USD) June: 487.1795; Expenditure 2022 (USD) OCTOBER: 25.641 | 512.8205 | 468.1319 | 52.28%
11006 | Regional Workshop (3) | 4017000 | 6376.1905 | 6535.9829 |  | Expenditure 2022 (USD) mai: 5957.8632; Expenditure 2022 (USD) June: 578.1197 | 6535.9829 | -159.7924 | 102.5%
11007 | launch brochures (2000) | 1442000 | 2288.8889 | 3025.641 |  | Expenditure 2022 (USD) July: 2897.4359; Expenditure 2022 (USD) OCTOBER: 128.2051 | 3025.641 | -736.7521 | 132.2%
11008 | Communication Web to SMS (2000) | 916288 | 1454.4254 | 0 | [13 empty] | 0 | 1454.4254 | 0%
11009 | Professional exchange events: BtoB, forum, networking, fair, etc. (6) | 19269734.4 | 30586.88 | 0 | [13 empty] | 0 | 30586.88 | 0%
11010 | Coaching for the development of the continuity plan for MSMEs (650) | 251062500 | 398511.9048 | 0 | [13 empty] | 0 | 398511.9048 | 0%
11011 | Coaching for the development of the continuity plan for Bas/ Lead firms (30) | 29355000 | 46595.2381 | 0 | [13 empty] | 0 | 46595.2381 | 0%
11012 | Training (Upgrading coaches for continuity plans) (1) | 1895200 | 3008.254 | 1081.5385 |  | Expenditure 2022 (USD) DECEMBRE: 1081.5385 | 1081.5385 | 1926.7155 | 35.95%
|  |  |  | 0 | [13 empty] | 0
| TOTAL Component 1: Business Resilience Capacity Building | 424976022.4 | 674565.1149 | 154993.9145 | 0 | 0 | 0 | 0 | 0 | 5957.8632 | 2165.2991 | 4962.3932 | 0 | 1593.547 | 30507.8889 | 9047.6923 | 100759.2308 | 154993.9145 | 519571.2004 | 22.98%
| Component 4: BRAVE IT Platform |  |  | 0 | 0 | [12 empty] | 0
41001 | IT officers (2) | 52019310.9055 | 82570.3348 | 33484.8325 | 0 |  |  | 1600.1504 | 3039.0513 | 4084.1761 | 3490.5983 | 3832.4786 | 3639.6581 | 3707.3504 | 4003.4188 | 4582.2684 | 1505.6821 | 33484.8325 | 49085.5023 | 40.55%
41003 | Acquisition of microsoft project | 82400 | 130.7937 | 111.1111 | 0 | Expenditure 2022 (USD) July: 105.5556; Expenditure 2022 (USD) OCTOBER: 5.5556 | 111.1111 | 19.6825 | 84.95%
41004 | Acquiring software and add-ons for the platform | 2060000 | 3269.8413 | 0 | 0 | [12 empty] | 0 | 3269.8413 | 0%
41005 | Add-on Development (1) | 3428973 | 5442.8143 | 721.3675 | 0 | Expenditure 2022 (USD) mai: 685.2991; Expenditure 2022 (USD) June: 0; Expenditure 2022 (USD) OCTOBER: 36.0684 | 721.3675 | 4721.4468 | 13.25%
41006 | Interfacing with MEBF ERP (1) | 5150000 | 8174.6032 | 0 | 0 | [12 empty] | 0 | 8174.6032 | 0%
| TOTAL Component 4: BRAVE COMPUTING Platform | 62740683.9055 | 99588.3872 | 34317.3111 | 0 | 0 | 0 | 1600.1504 | 3039.0513 | 4769.4752 | 3490.5983 | 3938.0342 | 3639.6581 | 3707.3504 | 4045.0427 | 4582.2684 | 1505.6821 | 34317.3111 | 65271.076 | 34.46%
| Composante 6: Executing Agency and Project Management Unit |  |  | 0 | [13 empty] | 0
61001 | Personnel costs | 277571890.0471 | 440590.3017 | 145414.8803 |  |  |  | 21415.5231 | 14588.6513 | 14885.6923 | 13300.5915 | 15042.9556 | 13918.8752 | 15585.9675 | 12958.4991 | 17703.6051 | 6014.5197 | 145414.8803 | 295175.4213 | 33%
61002 | Consultants: Mobile officer fees (4) | 36662904 | 58195.0857 | 0 | [13 empty] | 0 | 58195.0857 | 0%
63001 | UGP capacity building: knowledge transfer with Yemen (1) | 16686000 | 26485.7143 | 4575.5556 |  | Expenditure 2022 (USD) SEPTEMBER: 3534.5299; Expenditure 2022 (USD) OCTOBER: 974.359; Expenditure 2022 (USD) NOVEMBER: 66.6667 | 4575.5556 | 21910.1587 | 17.28%
63002 | Training of the team for the use of the IT platform (2) | 7247080 | 11503.3016 | 0 | [13 empty] | 0 | 11503.3016 | 0%
63003 | Costs of seminars conference, organization workshop (capitalization workshop) (1) | 10463635 | 16608.9444 | 0 | [13 empty] | 0 | 16608.9444 | 0%
63004 | Marketing and Promotion: press Insertion , (16) | 12570660.75 | 19953.4298 | 388.8889 |  | Expenditure 2022 (USD) DECEMBRE: 388.8889 | 388.8889 | 19564.5409 | 1.949%
63005 | Marketing and Promotion: Media Coverage (7) | 4051494.7 | 6430.944 | 0 | [13 empty] | 0 | 6430.944 | 0%
63006 | Marketing and Promotion: Spot Radio (3) | 309000 | 490.4762 | 0 | [13 empty] | 0 | 490.4762 | 0%
63007 | Marketing and Promotion: Diffusion radio spot (105) | 2575000 | 4087.3016 | 2202.0513 |  | Expenditure 2022 (USD) July: 2119.2325; Expenditure 2022 (USD) OCTOBER: 82.8188 | 2202.0513 | 1885.2503 | 53.88%
63008 | Marketing and Promotion: Spot TV (7) | 2621813.5 | 4161.6087 | 0 | [13 empty] | 0 | 4161.6087 | 0%
63009 | Marketing and Promotion: Diffusion spot TV (11) | 9962160 | 15812.9524 | 0 | [13 empty] | 0 | 15812.9524 | 0%
63010 | Marketing and promotion: production and distribution of video clips on success stories (12) | 19287162 | 30614.5429 | 0 | [13 empty] | 0 | 30614.5429 | 0%
63011 | Marketing and Promotion: Realization of capitalization materials (film) (1) | 6000000 | 9523.8095 | 0 | [13 empty] | 0 | 9523.8095 | 0%
63012 | Transport: transport and domestic movement / Burkina Faso | 376362 | 597.4 | 162.3932 |  | Expenditure 2022 (USD) mars: 46.1538; Expenditure 2022 (USD) mai: 73.5043; Expenditure 2022 (USD) June: 0; Expenditure 2022 (USD) DECEMBRE: 42.735 | 162.3932 | 435.0068 | 27.18%
63013 | Transport: Mission Expenses (Catering & Accommodation) permanent and transversal staff) | 29265436.35 | 46453.0736 | 35988.0342 |  |  |  | 769.2308 | 1435.8974 | 12176.0684 | 2991.453 | 6982.906 | 1589.7436 | 1333.3333 |  |  | 8709.4017 | 35988.0342 | 10465.0394 | 77.47%
63027 | Transportation: Travel expenses abroad | 12607200 | 20011.4286 | 42.735 |  | Expenditure 2022 (USD) AUGUST: 42.735 | 42.735 | 19968.6935 | 0.2136%
63014 | Consultants: Fees and remuneration of Intermediaries, advice, studies (evaluation and various studies) (2) | 12736362 | 20216.4476 | 0 | [13 empty] | 0 | 20216.4476 | 0%
63015 | Consultants: Remuneration for other services (translation) (200) | 4238717.8 | 6728.1235 | 0 | [13 empty] | 0 | 6728.1235 | 0%
63016 | Consultants: Recruitment costs and other remuneration (1) | 10000000 | 15873.0159 | 17428.7009 |  | Expenditure 2022 (USD) mars: 5542.9915; Expenditure 2022 (USD) April: 11240.7026; Expenditure 2022 (USD) mai: 645.0068 | 17428.7009 | -1555.685 | 109.8%
63017 | Consultants: Advisory Committee | 4775440.5 | 7580.0643 | 0 | [13 empty] | 0 | 7580.0643 | 0%
63018 | Consultants: Selection Committee | 1033862.5 | 1641.0516 | 753.8462 |  | Expenditure 2022 (USD) SEPTEMBER: 247.8632; Expenditure 2022 (USD) OCTOBER: 292.3077; Expenditure 2022 (USD) DECEMBRE: 213.6752 | 753.8462 | 887.2054 | 45.94%
63019 | Depreciation of the permanent vehicle | 19038108 | 30219.219 | 0 | [13 empty] | 0 | 30219.219 | 0%
| Depreciation of the additional vehicle | 2836898.1 | 4503.0129 | 0 | [13 empty] | 0 | 4503.0129 | 0%
63020 | Announcements and insertions, media coverage (Written radio-tv spots etc.) | 2309445.4 | 3665.7863 | 3042.4547 |  | Expenditure 2022 (USD) AUGUST: 2312.6889; Expenditure 2022 (USD) SEPTEMBER: 584.6154; Expenditure 2022 (USD) OCTOBER: 145.1504 | 3042.4547 | 623.3316 | 83%
63021 | Entertainment and cocktail fees | 2909709.006 | 4618.5857 | 1235.0427 |  | Expenditure 2022 (USD) April: 194.8718; Expenditure 2022 (USD) mai: 10.2564; Expenditure 2022 (USD) AUGUST: 85.4701; Expenditure 2022 (USD) SEPTEMBER: 751.0684; Expenditure 2022 (USD) OCTOBER: 39.5299; Expenditure 2022 (USD) DECEMBRE: 153.8462 | 1235.0427 | 3383.543 | 26.74%
63022 | Bank charges | 816179.05 | 1295.5223 | 691.9128 | 67.8735 |  | 9.5983 | 171.4222 | 51.8581 | 69.9573 | 27.5077 | 37.6291 | 41.6256 | 33.3607 | 38.5333 | 44.2291 | 98.3179 | 624.0393 | 603.6095 | 53.41%
63023 | Taxes | 316471.62 | 502.3359 | 0.25641 |  | Expenditure 2022 (USD) OCTOBER: 0.25641 | 0.25641 | 502.0795 | 0.05104%
63024 | Servicing, repair and maintenance | 6689924.16 | 10618.9272 | 10543.2974 |  |  |  | 350.4274 | 3191.0205 | 30.6974 |  | 3036.6376 | 145.2991 | 435.2137 | 22.906 |  | 3331.0957 | 10543.2974 | 75.6298 | 99.29%
63025 | Insurance premiums | 1318631.75 | 2093.0663 | 0 | [13 empty] | 0 | 2093.0663 | 0%
63026 | Computers, Equipment and Miscellaneous: office equipment + it + office furniture | 36379090.3407 | 57744.5878 | 55559.9145 |  | Expenditure 2022 (USD) June: 40743.6752; Expenditure 2022 (USD) SEPTEMBER: 14724.7863; Expenditure 2022 (USD) OCTOBER: 91.453 | 55559.9145 | 2184.6733 | 96.22%
64001 | Shopping | 33922187.89 | 53844.7427 | 21107.1402 |  | Expenditure 2022 (USD) April: 5814.1436; Expenditure 2022 (USD) mai: 46.8376; Expenditure 2022 (USD) June: 2273.5043; Expenditure 2022 (USD) AUGUST: 887.1795; Expenditure 2022 (USD) SEPTEMBER: 3660.6838; Expenditure 2022 (USD) OCTOBER: 7299.5829; Expenditure 2022 (USD) DECEMBRE: 1125.2085 | 21107.1402 | 32737.6025 | 39.2%
64002 | Transport of folds | 1636575.24 | 2597.7385 | 0 | [13 empty] | 0 | 2597.7385 | 0%
64003 | Miscellaneous rental charges | 1836629.05 | 2915.2842 | 256.4103 |  | Expenditure 2022 (USD) DECEMBRE: 256.4103 | 256.4103 | 2658.8739 | 8.795%
64004 | Rental of field offices | 9494148.6 | 15070.0771 | 1025.641 |  | Expenditure 2022 (USD) NOVEMBER: 1025.641 | 1025.641 | 14044.4361 | 6.806%
64005 | Telecommunications costs in the regions | 949414.86 | 1507.0077 | 0 | [13 empty] | 0 | 1507.0077 | 0%
64006 | Remuneration of external staf | 9185148.6 | 14579.601 | 0 | [13 empty] | 0 | 14579.601 | 0%
64007 | Other external charges (installation, moving) | 2060000 | 3269.8413 | 0 | [13 empty] | 0 | 3269.8413 | 0%
| TOTAL Composante 6: Executing Agency and Project Management Unit | 612740742.8138 | 972604.3537 | 300419.1556 | 67.8735 | 0 | 9.5983 | 28295.7487 | 36517.1453 | 27938.0205 | 59336.7316 | 27219.3607 | 19023.6171 | 40891.4222 | 21945.3966 | 18840.1419 | 20334.0991 | 300351.2821 | 672253.0716 | 30.89%
| TOTAL ACTIVITES +FONCTIONNEMENT | 1100457449.1194 | 1746757.8557 | 489730.3812 | 67.8735 | 0 | 9.5983 | 29895.8991 | 39556.1966 | 38665.359 | 64992.6291 | 36119.788 | 22663.2752 | 46192.3197 | 56498.3282 | 32470.1026 | 122599.012 | 489662.5077 | 1257095.3481 | 28.04%
65001 | Management fees | 335305530 | 532231 | 84653.4462 | 0 | 0 | 0 | 0 | 84166.2667 | 0 | 0 | 487.1795 | 0 | 0 |  |  |  | 84653.4462 | 447577.5538 | 15.91%
| MEBF Administrative Overhead | 239503950 | 380165 | 84653.4462 |  | Expenditure 2022 (USD) April: 84166.2667; Expenditure 2022 (USD) July: 487.1795 | 84653.4462 | 295511.5538 | 22.27%
| Security allowance | 95801580 | 152066 | 0 | [13 empty] | 0 | 152066 | 0%
66001 | Unexpected | 246791790 | 391733 | 0 | [13 empty] | 0 | 391733 | 0%
| TOTAL GENERAL | 1682554769.1194 | 2670721.8557 | 574383.8274 | 67.8735 | 0 | 9.5983 | 29895.8991 | 123722.4632 | 38665.359 | 64992.6291 | 36606.9675 | 22663.2752 | 46192.3197 | 56498.3282 | 32470.1026 | 122599.012 | 574315.9538 | 2096405.9019 | 21.51%
Le Comptable | [5 empty] | Expenditure 2022 (USD) NOVEMBER: Le Directeur de l'Administration
et des Finances
Ousmane DOULKOM | [5 empty] | Expenditure 2022 (USD) NOVEMBER: Sekou Dissa
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ici j'ai rajoute 8 tablettes et ordi informaticien

## Sheet1
activite | montant_budgetise | montant_depense 2021 2022 | T0 | T1 | T2 | T3
TOTAL composante 1 | 674565.1149 | 154993.9145 | 263148 | 259731
TOTAL composante 4 | 99588.3872 | 34317.3111 | 15872 | 15852 | 15852 | 15852
TOTAL Composante 6 | 1504835.3537 | 385004.7282 | 84021 | 84021 | 84021 | 84021
| 1604423.7408 | 574315.9538 | 363041 | 359604 | 99873 | 99873

## CASH FLOW STATEMENT
PROJECT NAME : BRAVE WOMEN
ORGANIZATION : Maison de l’Entreprise du Burkina Faso (MEBF)
PERIOD REPORTING : April 2021 to DECEMBER 2022
CASH FLOW STATEMENT
| YEARS | 2021 | 2022
| Months: |  | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31
A. Cash brought forward |  |  | -67.8735 | -67.8735 | -77.4718 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Contribution from ISDB |  | 2021-03-31: #REF!; 2021-12-31: #REF!
| B. Total Receipts | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
C. Payments | [15 empty] | 2021 |  | 2022
[15 empty] | COPOSANTE | 2021 | CUMUL | T1 | T2 | T3 | T4 | CUMUL
| Component 1: Business Resilience Capacity Building | 0 | 0 | 0 | 0 | 0 | 5957.8632 | 2165.2991 | 4962.3932 | 0 | 1593.547 | 30507.8889 | 9047.6923 | 100759.2308 | 1 | 0 | 0 | 0 | 8123.1624 | 6555.9402 | 140314.812 | 154993.9145
| TOTAL Component 4: BRAVE COMPUTING Platform | 0 | 0 | 0 | 1600.1504 | 3039.0513 | 4769.4752 | 3490.5983 | 3938.0342 | 3639.6581 | 3707.3504 | 4045.0427 | 4582.2684 | 1505.6821 | 4 | 0 | 0 | 1600.1504 | 11299.1248 | 11285.0427 | 10132.9932 | 34317.3111
| Composante 6: Executing Agency and Project Management Unit | 67.8735 | 0 | 9.5983 | 28295.7487 | 36517.1453 | 27938.0205 | 59336.7316 | 27706.5402 | 19023.6171 | 40891.4222 | 21945.3966 | 18840.1419 | 20334.0991 | 6 | 67.8735 | 67.8735 | 28305.347 | 207958.1641 | 87621.5795 | 61119.6376 | 385004.7282
[16 empty] | 67.8735 |  | 29905.4974 | 227380.4513 | 105462.5624 | 211567.4427 | 574315.9538
| MEBF Administrative Overhead |  | 2021-04-30: 84166.2667
Bank charges
| C. Total Payments | 67.8735 | 0 | 9.5983 | 29895.8991 | 123722.4632 | 38665.359 | 64992.6291 | 36606.9675 | 22663.2752 | 46192.3197 | 56498.3282 | 32470.1026 | 122599.012
574383.8274
D. Net Cashflow for the month |  | -67.8735 | -67.8735 | -77.4718 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cash carried forward |  | -67.8735 | -67.8735 | -77.4718 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Le Comptable |  | 2021-10-31: Le Directeur de l'Administration
et des Finances
| Ousmane DOUKOM |  | 2021-10-31: Sekou Dissa